## Slide 1: Session F: IATI financial update, funding model and fundraising
UNOPS
IATI Secretariat

## Slide 2: Year 1 in review
As trustee, UNOPS has negotiated, signed and received membership fees and voluntary contributions from 27 different organizations
This includes 4 instances of membership fees from the CSO category of membership
In the providers of development cooperation category this includes 21 such varying types of organization as OECD-DAC donor agencies, UN system entities, international financial institutions and foundations
This trust fund arrangement is currently the most diverse in terms of organization-type in UNOPS entire portfolio

## Slide 3: Year 1 financial update
The total amount received into the pooled IATI fund by the end of the programme year at 31 August 2014 was USD 2,089,707
Minus advance membership payments, the amount available for implementing activities was USD 1,831,569 (83% of the Y1 budget)
Of this, the amount spent implementing activities at 31 August 2014 was USD 1,596,426 (72% of the Y1 budget)
The amount currently committed and/or soon to be disbursed for final quarter activities is USD 188,171 (9% of the Y1 budget)
The amount remaining in the trust fund to be carried over to the Y2 opening balance is USD 46,971 (2% of the Y1 budget)

## Slide 4: Year 1 financial lessons learned
Cash flow has been identified as a significant issue with the membership fee model agreed to during Y1
Non-payment of fees and very late payment of fees by providers of development cooperation had two significant consequences:
  The full Y1 budget amount was not reached
  Receipt of some membership fees only in Q3/Q4 required a delayed start or postponement of activities to Year 2
In conclusion, while we thank the members who provided generous voluntary contributions in Y1 as trustee we urge the following:
  Some fine-tuning of the model presently agreed is required by members
  All members should endeavour to pay their fees in Q1 to improve the predictability of cash flow

## Slide 5: Year 2 financial forecast
The total amount need to be raised, excluding in-kind contributions, advance fee payments and other carryovers, to fully implement the Y2 workplan is USD 1,923,067
As trustee, we estimate that the as yet to be received Y2 membership fees will raise USD 910,116
  This is dependent on all Y1 payers meeting their Y2 obligations and includes the expected fees from the four Y1 non-paying members who have now indicated their ability to pay
This means that the amount that needs to be financed by voluntary contributions in Y2 is USD 1,012,951
Notes: 4 non-payers now offering to pay are:
New Zealand
Switzerland
The Global Fund
GAVI

## Slide 6: Fine-tuning the funding model
As trustee, we would advocate for some fine-tuning of the 70/30 model agreed to in March 2013:
  This is based on the lessons learned from the first year of implementing a theoretical model in a real-world context
  It also follows some analysis of a number of financial scenarios based on what funds can be predicted for Y2 though membership fees
Of actual contributions collected in Y1, more than half came from voluntary contributions
Looking at Y2 predictions, 53% will need to be raised from voluntary contributions

## Slide 7: Fine-tuning the funding model
The paper identifies two options for a decision by the members:
  Raising the level of the membership fee or;
  Accepting that 50% of what is needed for implementation will need to be raised from voluntary contributions
If the model is opened up to a greater dependency on voluntary contributions then this requires a more elaborate resource mobilization strategy

## Slide 8: Fundraising
The how - UNDP will develop a fundraising strategy in consultation with the Standing Sub-Group on Budget and Finance and with the support of a fundraising expert as an in-kind contribution by UNDP
The what - The annex to Paper 5 outlines some initial thinking about how to better incentivize voluntary contributions and suggests the following:
  Soft-earmarking workplan items to be underwritten by voluntary contributions
  Receiving financial contributions from outside the membership and including the private sector
  Branding enhancements

## Slide 9: Interlinked issues
Financial matters raised here should be understood as being deeply linked with and dependent on other Governance and Funding elements being discussed in Session F:
  Clarification of the status of members and observers
  Endorsement of the Y2 workplan